## Chart & Burndown
SCRUM PROJECT MANAGEMENT FIX THIS STUFF CHART
FIX THIS STUFF CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 6
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATED | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Setup and Infrastructure |  | 37 | 37 | 0 |  |  |  |  | 100%
1.1 | Configure Docker Compose with multi-database PostgreSQL | Antonino | 8 | 8 | 0 | 1 | 2025-04-21 | 2025-04-25 | 5 | 100% | bar: WEEK 1 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
1.2 | Setup RabbitMQ container for event-driven architecture | Leonardo | 5 | 5 | 0 | 1 | 2025-04-21 | 2025-04-23 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W; WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
1.3 | Setup API Gateway (Spring Boot) with routing configuration | Antonino | 8 | 8 | 0 | 1 | 2025-04-28 | 2025-05-02 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
1.4 | Initialize all microservices (auth, user, ticket, comment) | Mario + Leonardo | 10 | 10 | 0 | 1 | 2025-04-24 | 2025-05-02 | 9 | 100% | bar: WEEK 1 T to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
1.5 | Setup Vue 3 frontend project with Vite | Michel | 6 | 6 | 0 | 1 | 2025-04-21 | 2025-04-25 | 5 | 100% | bar: WEEK 1 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
2 | Authentication & Authorization System |  | 44 | 44 | 0 |  |  |  | 15 | 100%
2.1 | Implement user registration and login with bcrypt password hashing | Mario + Leonardo | 9 | 9 | 0 | 2 | 2025-05-05 | 2025-05-09 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F to WEEK 3 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
2.2 | JWT token generation and validation in API Gateway | Antonino | 9 | 9 | 0 | 2 | 2025-05-05 | 2025-05-09 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F to WEEK 3 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
2.3 | Create role-based middleware (USER, MODERATOR, ADMIN) | Antonino + Mario | 6 | 6 | 0 | 2 | 2025-05-12 | 2025-05-14 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 M to WEEK 4 T; WEEK 6 M to WEEK 6 T
2.4 | Build Login and Register views with form validation | Michel | 10 | 10 | 0 | 2 | 2025-04-28 | 2025-05-07 | 10 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F to WEEK 3 W; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
2.5 | Implement axios interceptors and route guards | Michel | 4 | 4 | 0 | 2 | 2025-05-08 | 2025-05-09 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 3 T to WEEK 3 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
2.6 | Containerize Flask API and consumer service | Leonardo | 4 | 4 | 0 | 2 | 2025-05-14 | 2025-05-15 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
2.7 | CORS configuration and cross-service authentication | Antonino | 2 | 2 | 0 | 2 | 2025-05-15 | 2025-05-15 | 1 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
3 | User Management & Role-Based Access |  | 55 | 55 | 0 |  |  |  | 33 | 100%
3.1 | Create users table with role constraints and default admin | Antonino | 1 | 1 | 0 | 3 | 2025-08-18 | 2025-08-18 | 1 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 M; WEEK 6 M to WEEK 6 T
3.2 | Implement user CRUD operations (list, view, update, delete) | Mario | 8 | 8 | 0 | 3 | 2025-08-19 | 2025-08-22 | 4 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 T to WEEK 6 T
3.3 | Create role assignment endpoints with authorization middleware | Antonino + Leonardo | 8 | 8 | 0 | 3 | 2025-08-19 | 2025-08-22 | 4 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 T to WEEK 6 T
3.4 | Implement role assignment UI with confirmation dialogs | Michel | 9 | 9 | 0 | 3 | 2025-08-20 | 2025-08-26 | 7 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 W to WEEK 6 T
3.5 | Build ProfileView and AdminView with user statistics and management | Michel + Antonino | 18 | 18 | 0 | 3 | 2025-08-26 | 2025-09-04 | 10 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 T to WEEK 6 T
3.6 | Implement cross-service user synchronization | Antonino + Mario | 9 | 9 | 0 | 3 | 2025-09-01 | 2025-09-05 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 M to WEEK 5 W
3.7 | Backend optimization and caching | Leonardo | 2 | 2 | 0 | 3 | 2025-08-25 | 2025-08-26 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 5 M to WEEK 5 T; WEEK 6 M to WEEK 6 T
4 | Ticket Management System |  | 62 | 62 | 0 |  |  |  | 90 | 100%
4.1 | Create ticket, topic, and junction tables with indexes | Antonino | 6 | 6 | 0 | 4 | 2025-09-08 | 2025-09-11 | 4 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 7 M to WEEK 7 T
4.2 | Implement ticket CRUD with filtering, search, and pagination | Mario + Antonino + Leonardo | 14 | 14 | 0 | 4 | 2025-09-10 | 2025-09-15 | 6 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 7 W to WEEK 8 F
4.3 | Add ticket assignment and moderator management features | Antonino | 8 | 8 | 0 | 4 | 2025-09-15 | 2025-09-17 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
4.4 | Create TicketView with with list, filters, and create form and edit/delete actions | Michel + Leonardo | 20 | 20 | 0 | 4 | 2025-09-10 | 2025-09-19 | 10 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 7 W to WEEK 8 F
4.5 | Implement ServiceRegistry for cross-service data enrichment | Antonino | 8 | 8 | 0 | 4 | 2025-09-16 | 2025-09-18 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
4.6 | Backend performance optimization | Leonardo | 6 | 6 | 0 | 4 | 2025-09-17 | 2025-09-19 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
5 | Comment System |  | 46 | 46 | 0 |  |  |  |  | 100%
5.1 | Create comment database schema and Flask Comment API | Leonardo | 12 | 12 | 0 | 5 | 2025-10-13 | 2025-10-20 | 8 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 8 M to WEEK 10 F
5.2 | Implement RabbitMQ event publishing (create/edit/delete) | Leonardo | 8 | 8 | 0 | 5 | 2025-10-20 | 2025-10-24 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
5.3 | Build Python consumer service for async persistence | Leonardo | 12 | 12 | 0 | 5 | 2025-10-20 | 2025-10-24 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
5.4 | Configure RabbitMQ exchanges and queues | Leonardo | 3 | 3 | 0 | 5 | 2025-10-21 | 2025-10-22 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
5.5 | Create comment UI components and integrate into TicketView | Michel + Antonino + Mario | 11 | 11 | 0 | 5 | 2025-10-20 | 2025-10-24 | 5 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
6 | Resolution Workflow, Leaderboard & Admin Features |  | 56 | 56 | 0 |  |  |  |  | 100%
6.1 | Implement resolution workflow (request/approve/reject) with anti-self-approval | Antonino | 12 | 12 | 0 | 6 | 2025-10-27 | 2025-11-03 | 8 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 10 M to WEEK 12 F
6.2 | Create developer_points table and point calculation logic | Antonino | 3 | 3 | 0 | 6 | 2025-11-03 | 2025-11-04 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
6.3 | Build public leaderboard endpoint ranked by points | Antonino | 6 | 6 | 0 | 6 | 2025-11-04 | 2025-11-07 | 4 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
6.4 | Implement ticket rating system (1-5 stars) | Mario | 8 | 8 | 0 | 6 | 2025-10-29 | 2025-11-05 | 8 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 11 W to WEEK 12 F
6.5 | Create PendingApprovalsView, LeaderboardView, and HomeView with statistics | Michel + Antonino + Leonardo + Mario | 5 | 5 | 0 | 6 | 2025-11-05 | 2025-11-06 | 2 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T
6.6 | Write comprehensive documentation (API, Architecture, Security) | Antonino + Mario + Leonardo + Michel | 22 | 22 | 0 | 6 | 2025-10-27 | 2025-11-07 | 12 | 100% | bar: WEEK 2 M to WEEK 2 W; WEEK 2 F; WEEK 4 W to WEEK 4 T; WEEK 6 M to WEEK 6 T; WEEK 10 M to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 300 | 300 | 0 | 58 | 5.1724 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 300 | 294.8276 | 289.6552 | 284.4828 | 279.3103 | 274.1379 | 268.9655 | 263.7931 | 258.6207 | 258.6207 | 253.4483 | 248.2759 | 243.1034 | 237.931 | 232.7586 | 227.5862 | 222.4138 | 217.2414 | 212.069 | 206.8966 | 201.7241 | 201.7241 | 196.5517 | 191.3793 | 186.2069 | 181.0345 | 175.8621 | 170.6897 | 165.5172 | 160.3448 | 155.1724 | 150 | 144.8276 | 139.6552 | 134.4828 | 129.3103 | 124.1379 | 118.9655 | 113.7931 | 108.6207 | 103.4483 | 98.2759 | 93.1034 | 87.931 | 82.7586 | 77.5862 | 72.4138 | 67.2414 | 62.069 | 56.8966 | 51.7241 | 46.5517 | 41.3793 | 36.2069 | 31.0345 | 25.8621 | 20.6897 | 15.5172 | 10.3448 | 5.1724
[10 empty] | ESTIMATE | 300 | 296 | 292 | 288 | 283 | 278 | 273 | 268 | 264 | 264 | 259 | 252 | 245 | 238 | 232 | 227 | 225 | 223 | 220 | 217 | 217 | 214 | 206 | 197 | 190 | 183 | 178 | 173 | 169 | 165 | 164 | 162 | 160 | 153 | 146 | 140 | 133 | 126 | 118 | 110 | 103 | 99 | 97 | 95 | 93 | 91 | 89 | 80 | 71 | 63 | 55 | 51 | 47 | 42 | 37 | 31 | 24 | 17 | 10 | 4 | 9647
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 0 | 5 | 7 | 7 | 7 | 6 | 5 | 2 | 2 | 3 | 3 | 0 | 3 | 8 | 9 | 7 | 7 | 5 | 5 | 4 | 4 | 1 | 2 | 2 | 7 | 7 | 6 | 7 | 7 | 8 | 8 | 7 | 4 | 2 | 2 | 2 | 2 | 2 | 9 | 9 | 8 | 8 | 4 | 4 | 5 | 5 | 6 | 7 | 7 | 7 | 6 | 4 | 300
[10 empty] | HRS REMAINING | 296 | 292 | 288 | 283 | 278 | 273 | 268 | 264 | 264 | 259 | 252 | 245 | 238 | 232 | 227 | 225 | 223 | 220 | 217 | 217 | 214 | 206 | 197 | 190 | 183 | 178 | 173 | 169 | 165 | 164 | 162 | 160 | 153 | 146 | 140 | 133 | 126 | 118 | 110 | 103 | 99 | 97 | 95 | 93 | 91 | 89 | 80 | 71 | 63 | 55 | 51 | 47 | 42 | 37 | 31 | 24 | 17 | 10 | 4 | 0 | 9347
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT FIX THIS STUFF CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have all the basics structure implemented and documentation ready |  | 40 | Completed |  | Not Started | 1
High | 2 | Implementing the Authentication and Authorization System | Backend Development | In this sprint our objective was to develop a registration and authentication system for the user |  | 40 | Completed |  | In Progress | 2
High | 3 | Implementing the User Management and Role-Based Access | Backend/Frontend Development | In this sprint our objective was to develop the user area with all the related user's action. |  | 60 | Completed |  | Completed | 4
High | 4 | Implementing the Ticket Management System | Backend/Frontend Development | In this sprint our objective was to develop a platform for the managing of the tickets |  | 60 | Completed |  |  | 8
High | 5 | Implementing the Comment System | Backend Development | In this sprint our objective was to implement a comment system |  | 40 | Completed |  |  | 16
Medium | 6 | Finalization of the system | Frontend Development,Finalization and testing | In this sprint I want to implement new features and make sure everything works without any error. |  | 60 | Completed |  |  | 24
40
60
80